## Title Page
CLC Assignment: Minesweeper MVC ASP Application
CST-247 : Enterprise Applications Programming III
1. Martin Carranza
2. Nicholas Thomas
3. Brian Cantrell
2020-11-22

## SprintProductLog
Project Title: CST247 Minesweeper MVC ASP Application
User Stories
ID | Feature | User Story | As a(n) <actor> | I would like to <description> | So that <outcome> | Priority | Sign-off Date | Modification Date
1 | Login Failed Page |  | User | Login failed status | Users know if they are logged in or not. | High | 2020-11-20
2 | Registration Failed Page |  | User | Registratin failed status | Users know if they did not register | High | 2020-11-20
3 | Reset Game |  | Developer | Reset the board if the user so decides to do so | So we can play more than 1 game during login | High | 2020-11-20
4 | Continue Game |  | Developer | Continue the game if the game is not over | So the user can continue a game they were playing | High | 2020-11-21
5 | Board Page |  | Developer | Display the game board after success login | The user can be greeted with the game to play | High | 2020-11-22
6 | Scoring logic |  | Developer | Show a score page after the game is over | The user understands where they rank compared to past players | High | N/A

## SprintBackLog
Project Title: CST247 Minesweeper MVC ASP Application Release #: 2.0 Sprint #: 2
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate | Assigned To
1 | Game Board | Developer | Display a Board upon login | So the user can play the game | 2h | Martin C.
2 | Reset Game | User | Reset the game | So the player can restart and play again | 1h | Martin C.
3 | Design Report/Scrum diagrams | Developer | Plan and design the project ahead of time | So there is an understanding of time allocated to parts of the project | 1h | Brian C.
4 | Wireframes | Developer | Build wireframes to mock pages | So its easy to understand what needs to be built in the views | 2h | Brian C.

## Burn Down Chart
Project Title: CST247 Minesweeper MVC ASP Application Release #: 1.2 Sprint #: 1.2 | [10 empty] | Total Days: | 7
User Stories
| Id | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Remaining
| 1 | Create game model view and controller | Create game model / view / controller | Martin | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
| 2 | Update time status for weeks progress | Product Log /Back Log | Brian | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| 3 | Create views for failed and successful login/register | Failed / Successful Views | Nicholas | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0
| 4 | Create DB tables for gameboard / reset continue game logic | Game DAO/ DB | Martin | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0
| 5 | Update the user interface with more game oriented home page and nav bar | Razor / Views Update | Brian | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| 6 | Update report status to track progress | Report / Wireframes | Brian | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 10 | 8.5714 | 7.1429 | 5.7143 | 4.2857 | 2.8571 | 1.4286 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 10 | 10 | 9 | 9 | 7 | 4 | 2 | 0

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time